## Slide 1
PRIMUS × MEGATRON-LM · PLAN-2 ROADMAP
DEEPSEEK-V4
in PRIMUS
Architecture-faithful rewrite. Megatron-native. Checkpoint-compatible.
v3.0 · 2026-05-01
PLAN-0 → PLAN-1 → PLAN-2

## Slide 2
DEVELOPMENT SCHEDULE
Day-by-day plan — 8 working days across two work blocks
Past block: Apr 28 → May 01 (landed). Holiday: May 02 → 05 (skipped). Plan-2 block: May 06 → 09.
May 2-5 HOLIDAY
Apr 28
Tue · DONE
P0 ~ P7
MVP bring-up
Investigation + tech blog
YAML configs (base / Flash / Pro)
model_type dispatch + builder
HC + Hybrid Attn + MoE/MTP
1×8 PP=2 EP=4 BF16 smoke
Apr 29
Wed · DONE
P8
ModuleSpec refactor
Spec-driven runtime path
DeepseekV4Model on LanguageModule
Builder routes V4 spec only
Retire GPT-placeholder swap
Apr 30
Thu · DONE
P9 ~ P10
TE provider + MoE bridge
DeepSeekV4SpecProvider
Norm + projection providerized
MoE submodules + dispatcher
EP all-reduce fallback gated
A/B local↔TE forward report
May 01
Fri · DONE
P12
Plan-2 lockdown
Architecture review
10 CRIT / 11 HIGH findings
plan-2/00..04 + README
status.md P12+ section
timeline.html + PPT roadmap
May 06
Tue · PLAN
P13 ~ P14
Faithful attn + MoE
DeepseekV4Attention(MLA)
Single-latent KV (wkv)
q_norm / kv_norm / sink
Grouped low-rank O proj
ClampedSwiGLU pre-mul
Hash + learned routers
May 07
Wed · PLAN
P15 ~ P16
Layer/Block/HC×PP + MTP
DeepseekV4HybridLayer(TL)
DeepseekV4Block(TB)
[S,B,K,D] PP packing
HyperHead on post_process
MultiTokenPredictionBlock
process_mtp_loss wired
May 08
Thu · PLAN
P17 ~ P18
Checkpoint + spec audit
HF→Primus state-dict map
load_v4_flash_check.py
tid2eid as buffer
Round-trip + token-0 align
Provider per build call
compress_ratios → list
May 09
Fri · PLAN
P19 ~ P21
Validation + release
TP/PP/EP smoke grid
Routing snapshot diff = 0
G9 numerical alignment
200-step convergence vs HF
TE on/off perf report
Cleanup + tag + handover
BLOCK A · Apr 28 → May 01 · 4 days · landed
BLOCK B · May 06 → May 09 · 4 days · plan-2 execution
DeepSeek-V4 × Primus · Plan-2 Roadmap
08 / 13

## Slide 3
01 · EXECUTIVE OVERVIEW
Three plans, one model, one mission
Where we have been, where we are, and what plan-2 must deliver.
PLAN-0
P0 → P7
Bring-up
DONE
Architecture investigation
YAML configs (Flash / Pro)
model_type dispatch in trainer
Initial layer specs / block
HC + hybrid attention scaffold
MoE / activation / RoPE / MTP
Single-node smoke runnable
PLAN-1
P8 → P11
ModuleSpec convergence
PARTIAL · PAUSED
Spec/provider refactor (P9) ✓
TE / Turbo provider reuse (P10) ✓
MoE distributed convergence (P11) –
Hash router still reinvented
Attention still nn.Module
No state-dict adapter
Real V4 parity NOT achieved
PLAN-2
P12 → P21
Architecture-faithful rewrite
ACTIVE
Rebase on MLASelfAttention
TransformerLayer / Block reuse
MoELayer / TopKRouter reuse
MultiTokenPredictionBlock reuse
Faithful HC with PP-aware fix
State-dict adapter (HF → primus)
Numerical alignment release gate
P0 – P11
Phases shipped
P12 – P21
Phases re-planned
10
CRIT findings
11
HIGH findings
+8
Reused MCore modules
DeepSeek-V4 × Primus · Plan-2 Roadmap
02 / 13

## Slide 4
02 · WHAT MAKES DEEPSEEK-V4 HARD
The architectural surface we must reproduce
Six axes where V4 diverges from a vanilla MoE transformer.
01
Hyper-Connections (HC)
K parallel residual streams with a learnable Sinkhorn-normalised mixer per layer. Splits input into K paths, mixes after each block, collapses at the head.
02
Hybrid Attention
Mix of Dense / Compressed-Sparse Attn (CSA) / Heavily-Compressed Attn (HCA). Single-latent KV (K=V), per-head q_norm + kv_norm, grouped low-rank O.
03
MoE: Hash + Learned
Hash router for some layers, learnable router with sqrtsoftplus / sigmoid / softmax score for others. Shared experts, expert bias, Megatron MoE dispatch.
04
Clamped SwiGLU
PRE-multiplication clamp on silu(gate) and up before the elementwise multiply (not post-mul). Distinct w1 / w3 weights — no fused gate-up.
05
Dual-RoPE + YaRN
Two RoPE caches (main, compress) with different theta, partial-RoPE on first dim, YaRN scaling on the compressed path.
06
Multi-Token Prediction
Auxiliary lookahead heads on top of the main decoder. Must reuse Megatron's MultiTokenPredictionBlock for PP / loss / activation checkpointing.
DeepSeek-V4 × Primus · Plan-2 Roadmap
03 / 13

## Slide 5
03 · CODE REVIEW FINDINGS
What's wrong on dev/wenx/deepseek-v4 today
Severity-ranked findings from the e194e039..HEAD review.
CRIT
Architecture diverges from real V4
HIGH
Distributed / spec correctness
MED
Megatron reuse / hygiene
LOW
Style / docs / coverage
A1
CRIT
Attention uses separate K/V projections (real V4 has single wkv = single-latent MQA).
A2
CRIT
Missing per-head q_norm / kv_norm RMSNorms after the low-rank projections.
A3
CRIT
HashRouter has no learnable gate weight; outputs uniform 1/topk instead of learned scores.
A4
CRIT
Clamped SwiGLU clamps post-mul — real V4 clamps pre-mul on silu(gate) and up.
A5
CRIT
No state-dict adapter — official HF / V4-Flash checkpoints cannot be loaded.
A6
HIGH
HCAAttention RoPE: position_id calculation for compressed layers is off.
B1
HIGH
DeepseekV4Attention is plain nn.Module, not a MLASelfAttention subclass.
B2
HIGH
DeepseekV4TransformerBlock does not subclass TransformerBlock.
B3
HIGH
DeepseekV4HybridLayer does not subclass TransformerLayer.
B4
HIGH
DeepseekV4MoE does not subclass MoELayer; reinvents dispatch wiring.
C1
HIGH
HC × PP: HyperHead applied per stage, destroys K-stream context across PP boundary.
C2
HIGH
Token-IDs stashed on decoder._v4_token_ids — breaks PP, leaks stale state.
C3
MED
Position IDs faked internally; caller-supplied position_ids ignored.
C4
MED
TP partitioning of attention low-rank uses 'duplicated' instead of sharded.
D1
MED
Compressor / Indexer / DualRoPE not expressed as spec submodules.
D2
MED
MTP bypasses MultiTokenPredictionBlock; reimplements PP-incompatible variant.
E1
LOW
compress_ratios stored as string in YAML, parsed by ast.literal_eval.
E2
LOW
No numerical alignment harness vs HF or NeMo reference.
DeepSeek-V4 × Primus · Plan-2 Roadmap
04 / 13

## Slide 6
04 · PLAN-2 STRATEGY
Three pillars: faithful · native · verifiable
Reuse Megatron, parity with reference, gated by numerical tests.
01
Megatron-Native
Subclass MLASelfAttention, TransformerLayer,
TransformerBlock, MoELayer, TopKRouter,
MultiTokenPredictionBlock, YarnRotaryEmbedding.
Express V4 extensions as ModuleSpec submodules:
Compressor / Indexer / DualRoPE / HyperMixer.
02
Architecture-Faithful
Single-latent KV (wkv), per-head q/kv_norm,
grouped low-rank O, attention-sink scalar.
HashRouter as a TopKRouter with frozen gate.
Pre-mul clamping for SwiGLU; w1/w3 unfused.
HC fixed across PP via stream-packed send/recv.
03
Verifiable
State-dict adapter: HF → Primus weight names.
Numerical-alignment harness vs HF reference.
Distributed smokes: TP/PP/EP grids, MTP on/off.
Release gates G1..G13 — every phase contributes.
All gates green before P21 / release.
GUIDING PRINCIPLES · reuse > reinvent · spec > monolith · parity > perf · tests gate phases
DeepSeek-V4 × Primus · Plan-2 Roadmap
05 / 13

## Slide 7
05 · PLAN-2 PHASE BREAKDOWN
Ten phases — P12 lockdown to P21 release
Each phase has explicit deliverables, exit criteria, and a release gate.
PHASE
NAME
DELIVERABLE
TYPE
P12
Lockdown
Plan-2 scope sign-off; status.md / dashboards updated.
DOC
P13
Faithful Attention
DeepseekV4Attention(MLASelfAttention) with single-latent KV, q/kv_norm, grouped O, sink scalar.
CODE
P14
MoE & Activation
HashRouter as TopKRouter subclass; learned router with sqrtsoftplus; pre-mul clamp; ClampedSwiGLU MLP.
CODE
P15
Layer · Block · HC×PP
DeepseekV4Layer(TransformerLayer); TransformerBlock subclass; HC stream-packed PP send/recv.
CODE
P16
MTP integration
Plug into MultiTokenPredictionBlock; lookahead heads PP-aware; per-head loss aggregation.
CODE
P17
State-dict Adapter
HF V4-Flash / V4-Pro → Primus weight name map; round-trip load/save tested.
CODE
P18
Spec System Audit
All V4 modules expressed as ModuleSpec submodules; build_module path everywhere; provider audit.
REFACTOR
P19
Distributed Re-validation
TP / PP / EP grid smoke; MTP on/off; HC=K1..K4; FP8 toggles; all gates G1..G11.
TEST
P20
Release Gates & Cleanup
Numerical alignment vs HF reference; gate G12 / G13 green; deslop pass.
TEST
P21
Tag & Handoff
Tag v4.0; tech-blog publish; pretrain checkpoint hand-off to convergence team.
RELEASE
DeepSeek-V4 × Primus · Plan-2 Roadmap
06 / 13

## Slide 8
06 · DEPENDENCY GRAPH
How plan-2 phases unlock each other
Arrows = hard dependencies. Nodes group around three swimlanes.
MODULES
INTEGRATION
VALIDATION
P12
Lockdown
P13
Faithful Attn
P14
MoE / Activ.
P15
Layer / Block / HC×PP
P16
MTP
P17
State-dict
P18
Spec audit
P19
Dist. re-valid.
P20
Release gates
P21
Tag
Module work
Integration / refactor
Validation / release
Risk gate
DeepSeek-V4 × Primus · Plan-2 Roadmap
07 / 13

## Slide 9
08 · TIMELINE
Three plans on one bar chart
Calendar weeks; light bars = done, neon bars = active / planned.
W17
W18
W19
W20
W21
W22
W23
W24
W25
W26
W27
W28
W29
W30
P0 Investigation
DONE
P1 Configs
DONE
P2 model_type
DONE
P3 Layer specs
DONE
P4 HC + Hybrid Attn
DONE
P5 MoE / RoPE / MTP
DONE
P6 Trainer e2e
DONE
P7 Single-node smoke
DONE
P8 Plan-1 scoping
P9 Spec refactor
DONE
P10 TE provider
DONE
P11 MoE distrib.
PARTIAL
P12 Plan-2 lockdown
ACTIVE
P13 Faithful attn
TODO
P14 MoE & activ.
TODO
P15 Layer / HC×PP
TODO
P16 MTP
TODO
P17 State-dict
TODO
P18 Spec audit
TODO
P19 Dist. revalid.
TODO
P20 Release gates
TODO
P21 Tag & handoff
TODO
done
partial
active
planned
DeepSeek-V4 × Primus · Plan-2 Roadmap
09 / 13

## Slide 10
09 · MILESTONES & RISKS
What success looks like — and what could derail it
Stakeholder communication checkpoints + the top-3 things keeping us up at night.
MILESTONES
M1
Plan-2 sign-off
End P12
M2
Faithful attention green
End P13 — gate G3
M3
MoE / activation parity
End P14 — gate G5
M4
PP-aware HC verified
End P15 — gate G7
M5
HF checkpoint loadable
End P17 — gate G9
M6
All distributed grids green
End P19 — gate G11
M7
Numerical alignment ≤1e-3
End P20 — gate G13
M8
v4.0 tag & blog published
End P21
TOP RISKS
R1
Real V4 reference drift
HF reference and NeMo diverge on partial-RoPE pairing and HC head application; we may need two compatibility modes.
R2
HC × PP correctness
K-stream packing across PP boundaries hasn't been done in MCore; needs custom send/recv tensor schema.
R3
State-dict ABI
Per-head q_norm / kv_norm naming differs between HF and NeMo; must lock canonical naming before P17.
R4
FP8 / Turbo regressions
Re-rooting attention on MLASelfAttention may break TE / Turbo quantised paths. Needs explicit P19 grid.
R5
Numerical-alignment thresholds
Mixing TE FP8 + ClampedSwiGLU + sinkhorn HC produces noise > 1e-3. Need calibrated thresholds per gate.
DeepSeek-V4 × Primus · Plan-2 Roadmap
10 / 13

## Slide 11
10 · TEST STRATEGY
Four levels, thirteen gates, one release
Each phase contributes tests; nothing ships without G1..G13 green.
L0
Unit
RoPE / RMSNorm exactness
ClampedSwiGLU pre-mul clamp
TopKRouter scores
HashRouter tid2eid stability
L1
Module integration
MLA single-latent KV
Compressor / Indexer wiring
DualRoPE on attention block
MoE dispatcher round-trip
L2
Distributed smoke
TP=2/4 ; PP=2/4 ; EP=4/8
MTP on/off
HC K=1..4
Activation checkpoint on/off
FP8 Turbo on/off
L3
Release gate
HF reference numerical align ≤ 1e-3
Checkpoint round-trip
Loss curve sanity (toy)
Throughput vs Plan-1 ≥ 0.95×
RELEASE GATES
G1 build
G2 lint
G3 attn
G4 csa/hca
G5 moe
G6 swiglu
G7 hc-pp
G8 mtp
G9 ckpt
G10 spec
G11 dist
G12 align
G13 release
DeepSeek-V4 × Primus · Plan-2 Roadmap
11 / 13

## Slide 12
11 · CURRENT STATUS & NEXT-2-WEEKS
Where we are today and what lands next
Snapshot taken 2026-05-01 against branch dev/wenx/deepseek-v4.
TODAY · PLAN-2 LOCKDOWN
✓
Architecture review done
10 CRIT / 11 HIGH / 6 MED / 5 LOW
✓
Plan-2 docs landed
README + 00..04 in plan-2/
✓
status.md updated
P12 lockdown row appended
✓
Timeline HTML
progress/timeline.html
⟶
Awaiting sign-off
stakeholder review of plan-2 scope
⟶
Tech-blog rollover
as-built notes for plan-1 + pointer to plan-2
NEXT 4 WORKDAYS · MAY 06 → MAY 09
May 06
P13 + P14 · Faithful attn + MoE
MLA-rooted attn with single-latent KV / q+kv norm / grouped O / sink. Hash + learned routers; pre-mul ClampedSwiGLU.
May 07
P15 + P16 · Layer/Block + MTP
DeepseekV4HybridLayer(TL) + Block(TB) with [S,B,K,D] PP packing. MultiTokenPredictionBlock + per-MTP HyperHead.
May 08
P17 + P18 · Checkpoint + spec audit
HF→Primus state-dict adapter; load V4-Flash; provider-built-once contract; YAML compress_ratios → list.
May 09
P19 + P20 + P21 · Validate + ship
TP/PP/EP grid smoke; 200-step convergence vs HF; TE on/off perf report; cleanup + tag + handover.
DeepSeek-V4 × Primus · Plan-2 Roadmap
12 / 13

## Slide 13
READY FOR PLAN-2
Let's build
a real DeepSeek-V4.
Documents: deepseek-v4/develop/plan-2/ · Progress: deepseek-v4/develop/progress/
13 / 13